## Project Planner
Project 20 Planner
Period Highlight: |  |  |  |  | Period Highlight: | 22 |  |  | Plan Duration |  |  |  |  | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [5 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS |  | 2020-10-05 |  | 2020-11-02 |  |  |  | 2020-11-30 |  |  |  | 2020-12-28 |  |  |  | 2021-01-25 |  |  |  | 2021-02-22 |  |  |  | 2021-03-22
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
1. Research | 1 | 4 | 1 | 8 | 100%
1.1 Background research | 1 | 4 | 1 | 4 | 100%
1.2 Group page | 2 | 2 | 2 | 2 | 100%
1.3 Technical research | 5 | 1 | 7 | 2 | 100%
1.3 User research | 6 | 1 | 6 | 2 | 100%
2. Design | 7 | 3 | 6 | 4 | 100%
2.1 Write requirements | 7 | 2 | 7 | 2 | 100%
2.2 Design prototypes | 7 | 3 | 6 | 3 | 100%
2.3 Architectural design | 8 | 2 | 7 | 3 | 100%
2.4 Outline planning | 9 | 1 | 9 | 1 | 100%
2.5 GUI design | 9 | 1 | 8 | 2 | 100%
3. Implementation | 10 | 12 | 14
3.1 Create testing structure | 10 | 2 | 14 | 1 | 100%
3.2 Learn related knowledge | 15 | 2 | 15 | 2 | 100%
3.3 Make basic components | 16 | 1 | 16 | 1 | 100%
3.4 UI for start page & subpages | 16 | 1 | 16 | 1 | 100%
3.5 make swap animation | 17 | 1 | 16 | 1 | 100%
3.6 Bubble sort algorithm | 17 | 1 | 17 | 1 | 100%
3.7 Router feat & local storage | 17 | 1 | 17 | 1 | 100%
3.8 Animate 2 algorithms (SI) | 17 | 1 | 17 | 1 | 100%
3.9 Help and setting | 17 | 1 | 17 | 1 | 100%
3.10 Correctness proposal | 18 | 1 | 18 | 1 | 100%
3.11 improve ui with electron | 18 | 1 | 18 | 1 | 100%
3.12 animate merge and heap | 18 | 1 | 18 | 4 | 100%
3.13 refactor previous work | 20 | 1 | 20 | 2 | 100%
3.14 design correctness part | 20 | 1 | 20 | 2 | 100%
3.15 correctness tutorial | 21 | 1 | 21 |  | 90%
3.16 Tutorial design | 22 | 1 | 22 | 1 | 100%
3.17 Tutorial pages | 23 | 2 | 23 |  | 66%
3.18 Procedure imple | 23 | 2 | 23 |  | 60%
3.19 Improve transition anime | 24 | 1 | 24
3.20 Refactor previous work | 24 | 1 | 24
3.21 Correctness proof | 24 | 1
3.7 Test algorithm correctness | 21 | 3 |  | 2 | 0%
3.8 Practice feature | 19 | 2 |  |  | 0%
3.9 Additional features | 20 | 2 |  |  | 0%
3.10 Optimise features | 21 | 1 |  |  | 0%
4. Reports
4.1 Interim Report | 5 | 4 | 5 | 5 | 100%
4.2 Final Report | 22 | 6 | 22 |  | 25%
4.3 Individual Report | 22 | 7 |  |  | 0%
5. Testing | 21 | 6
5.1 Release testing | 21 | 3 |  |  | 0%
5.2 Acceptance testing | 24 | 3 |  |  | 0%
6. Evaluation | 21 | 8
6.1 Software demonstration | 21 | 3 |  |  | 0%
6.2 Team presentation | 23 | 3 |  |  | 0%
6.3 Promotional digital artefact | 25 | 3 |  |  | 0%
6.4 End of project | 28 | 1 |  |  | 0%